## Sheet1
Feature | Sub Feature | Back-end | Assumptions
Main Portal
Project Setup |  | 5
Layout | Header & Navigation Menu | 4
| Footer | 2
APIs (For Front-end Application) | Design | 1
| Configuration and setup | 1
| Authentication | 2
| Documentation | 1
Home Page | Setup and configurations | 1
| Banner Section | 1
| KPIs Section | 1
| GAFI Services Section ( section back-office + View) | 1
| Promotional Sectors | 1
| Egypt is Ready (Reasons to Invest) | 1
| News Section | 1
| Events Section | 1
| Success Stories Section | 1
| Investors Support (We are here to help you) | 1
| Testimonials Section | 1
| Partners Section | 1
Banner | Back-office | 1.5
KPIs | Back-office | 1
GAFI Services | Back-office | 2
| Listing | 1
| Details Pages (2 Templates) | 4
Promotional Sectors | Back-office | 1.5
| Listing and details pages | 3
Egypt is Ready (Reasons to Invest) | Back-office | 1.5
News | Backoffice + categories | 1.5
| Listing and details APIs | 3
Events | Backoffice + categories | 1.5
| Listing and details APIs | 3
Contact us | Content page + Social media details | 1 | * Submissions will not be stored in the CMS.
| CRM Integration | 2
| Form, submit and send email | 2
Success Stories | Back-office | 1.5
| Listing and details APIs | 3
Investors Support (We are here to help you) | Useful Links ( Back-office + API ) | 2
| FAQs ( Back-office + API ) | 2
Service Catalog (Discover Our Services) | Back-office + Categories | 2
| Listing page | 2
| Details page | 2
Virtual Library | Back-office | 1 | * GAFI is responsible for converting PDFs into flipbooks and providing an embed code (iframe or script). This code can be entered via the backoffice.
| Listing Page | 1.5
| Details Page | 1
Media Library | Back-office | 1.5
| Listing Page | 1.5
| Details Page | 1
Eligibility | Form + Validations + Submission | 2
| Save and view Submissions | 3
| Emails | 1
Content pages | 5 templates | 10
Search |  | 5 | * Search functionality will return results only from content in the language currently selected by the user.
Partners | Backoffice + categories | 1.5
| Listing and details APIs | 3
Testimonials | Backoffice + categories | 1.5
| Listing and details APIs | 3
Publications | Backoffice + categories | 1.5 | * Assumed to have title, description, body, date, category and document
| Listing and details APIs | 3
Home Page Static Map | Back-office | 4
| Data API | 3
Admin user roles and permissions |  | 3
Admin users management |  | 2
Lookups | Up to 5 | 3
Privacy policy + Terms and Conditions |  | 1
Settings Page | Back-office + APIs | 3
Sitemap |  | 1
Breadcrumb |  | 2
SSO |  | 15 | * Requires a Strapi Enterprise license.
Non-Functional
Multilanguage |  | 5 | * Arabic and English for the public portal * English only for the admin panel (Back-office)
HTTP Error Pages |  | 1
SEO |  | 5
GDPR |  | 3
Performance |  | 5
Security |  | 10
Environment (Dev, Testing and staging) |  | 15
Reviews |  | 5
Demos |  | 5
Data Migrations | up to 5 templates | 10 | * Estimates are provided for migrating selected content types or lookups that can be exported from the old SharePoint portal in CSV/Excel format such as News, Events. * Single pages (one of type pages) will be manually migrated by the content editing team.
Production Deployment |  | 5
UAT |  | 15
Total |  | 235
10.6818